## Sheet1
Package | Use Case | Task | Estimate | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10
Startup
Startup
|  | Analysis | 3
|  | Design | 3
|  | Development | 4
|  | Test | 3
Play Game
Move
|  | Analysis | 3
|  | Design | 3
|  | Development | 4
|  | Test | 6
Use Item
|  | Analysis | 2
|  | Design | 1
|  | Development | 2
|  | Test | 2
Battle
|  | Analysis | 2
|  | Design | 1
|  | Development | 2
|  | Test | 2
Manage World
Create World
|  | Analysis | 5
|  | Design | 3
|  | Development | 8
|  | Test | 5
Join World
|  | Analysis | 2
|  | Design | 2
|  | Development | 1
|  | Test | 1
Delete World
|  | Analysis | 2
|  | Design | 1
|  | Development | 1
|  | Test | 1
Manage Player
Login
|  | Analysis | 2
|  | Design | 2
|  | Development | 1
|  | Test | 1
Manage Character
|  | Analysis | 3
|  | Design | 3
|  | Development | 4
|  | Test | 3
Invite Player to World
|  | Analysis | 1
|  | Design | 1
|  | Development | 1
|  | Test | 1
Player Management
|  | Analysis | 2
|  | Design | 2
|  | Development | 3
|  | Test | 1
Maintenance
Report Error
|  | Analysis | 1
|  | Design | 2
|  | Development | 2
|  | Test | 1
Add New Feature
|  | Analysis | 2
|  | Design | 2
|  | Development | 4
|  | Test | 2
Error Resolution
|  | Analysis | 2
|  | Design | 2
|  | Development | 2
|  | Test | 1
Integration
| Testing | Stream 1 | 7
|  | Stream 2 | 7
| Resource 1 | Business resource
| Resource 2 | Business resource
| Resource 3 | Development resource
| Resource 4 | Development resource
| Resource 6 | Test resource
| Resource 7 | Test resource